## Sheet1
Sangam updates:
Plan:(step wise)
1. CPM model making with wood
2. CPM model making with metal
3. linear actuator and button integration
END OF STAGE 1
4. Force sensor integration
5. calibration of sensors
6. providing feedback to linear actuator
7. providing feedback to game
8. vibrator motor integration
END OF STAGE 2
9. stage 1 and stage 2 integration
10. giving a product like finish
11. Testing and error correction
work sessions | pramoth | viekash | gaurav | manimozhi | REMARKS
2008-01-01 | game dev | work on mechanics | work on mechanics | design the model
2009-01-01 | game dev | work on mechanics | work on mechanics | design the model
2011-01-01 | game dev | seggregate components and test them | fab | fab
2012-01-01 | button integration | button integration | fab | fab
2013-01-01 | game dev | arduino coding and calibration | fab | fab | completion of step 1 and step 3
2016-01-01 | game dev | fab | fab | fab
2018-01-01 | game dev | fab | fab | fab
2019-01-01 | game integration with arduino | fab | fab | fab | completion of step 2
2020-01-01 | completion of 4-5 levels of game | force sensor integration | force sensor integration | force sensor integration | completion of step 4
2023-01-01 | developing rest of the levels of game | calibration | calibration | calibration
2024-01-01 | developing rest of the levels of game | calibration | calibration | calibration | completion of step 5 and 6
2025-01-01 | developing rest of the levels of game | vibrator motor integration | vibrator motor integration | vibrator motor integration | completion of step 8
2026-01-01 | developing rest of the levels of game | testing and error correction | testing and error correction | testing and error correction
2029-01-01 | testing and error correction | testing and error correction | testing and error correction | testing and error correction | completion of step 7, game dev done (15 levels)
1931-01-01 | testing and error correction | testing and error correction | testing and error correction | testing and error correction | completion of step 9
2001-02-01 | testing and error correction | testing and error correction | testing and error correction | testing and error correction | completion of step 10
2004-02-01 | testing and error correction | testing and error correction | testing and error correction | testing and error correction | completion of step 11
TIME LINE | WORK TO BE DONE
jan 8 - 11 | mechanics, model design, component collection,game dev
jan 12 - 21 | fabrication with wood and electronics side by side, game dev
jan 22 -25 | force sensor, vibrator mo and coding respectively
jan 26 - feb 4 | testing and error correction
feb 5 - feb 15 | upgrade it to metal body and repeat all the steps
feb 16 - march 5 | testing and error correction